## About_the_toolkit
This toolkit is a practical, audit-ready compliance tool that translates the CBUAE Climate-related Financial Risk Management Regulation (Circular 8/2025) into a structured, end-to-end checklist system for banks and insurers. It consolidates all key requirements into a single master Checklist with clear ownership, frequency, target dates, evidence references, and implementation status; links gaps automatically into a Remediation Plan with actions, milestones, and due dates; maintains an Evidence Register to standardize what documents, dashboards, minutes, models, and policies prove compliance; and tracks climate Metrics/KRIs to demonstrate measurable governance and risk management maturity. A formula-driven Dashboard pulls live results across the tabs (completion rate, overdue items, evidence gaps, and readiness indicators), so leadership can see where compliance is strong, where controls are missing, and what must be fixed next, without manual reporting.

## Dashboard
CBUAE Climate Risk Compliance — Implementation Dashboard
Total Requirements | 35 |  | Requirements missing Evidence_ID | 0
Implemented | 2 |  | Overdue Targets (Checklist) | 0
In Progress | 19 |  | Open Remediation Actions | 10
Not Started | 13 |  | Overdue Remediation Actions | 0
Blocked | 1 |  | Metrics with Data Available | 4
Overall Completion % | 5.714% |  | Metrics Missing Data | 2
Completion by Article
Article | Total | Implemented | Completion %
Art 1 | 2 | 1 | 50%
Art 2 | 7 | 1 | 14.29%
Art 3 | 2 | 0 | 0%
Art 4 | 19 | 0 | 0%
Art 5 | 2 | 0 | 0%
Art 6 | 2 | 0 | 0%
Art 7-8 | 1 | 0 | 0%
Status Distribution
Status | Count
Implemented | 2
In Progress | 19
Not Started | 13
Blocked | 1

## Checklist
Req_ID | Domain | Article | Clause | Requirement (Control Objective) | Owner | Frequency | Evidence_ID | Status | Target_Date | Completion_Date | Notes
CBUAE-001 | Applicability | Art 1 | 1.1 | Confirm institution is in-scope and define compliance perimeter (solo + group-wide where applicable). | Compliance | Annual | EV-001 | Implemented | 2026-04-15 | 2026-02-02
CBUAE-002 | Applicability | Art 1 | 1.2 | Document proportionality approach (how requirements are met given size/complexity). | CRO | Annual | EV-002 | In Progress | 2026-05-15
CBUAE-003 | Governance | Art 2 | 2.1 | Board approved climate-risk governance framework and assigns ultimate accountability. | Board Secretariat | Annual | EV-003 | Implemented | 2026-06-14 | 2026-02-22
CBUAE-004 | Governance | Art 2 | 2.2 | Board and senior management maintain climate competence (skills matrix + annual training plan). | HR / L&D | Quarterly | EV-004 | In Progress | 2026-07-14
CBUAE-005 | Governance | Art 2 | 2.3 | Board receives decision-useful dashboards on climate exposures and approves climate risk appetite at least annually. | CRO | Quarterly | EV-005 | In Progress | 2026-08-13
CBUAE-006 | Governance | Art 2 | 2.4 | Committee mandates updated (Risk/Audit/Remuneration) to include climate responsibilities and escalation routes. | Board Secretariat | Annual | EV-006 | Not Started | 2026-03-16
CBUAE-007 | Governance | Art 2 | 2.5 | Resourcing plan approved (budget, roles, expertise) for climate risk implementation. | CRO | Annual | EV-007 | In Progress | 2026-04-15
CBUAE-008 | Governance | Art 2 | 2.6 | Green/ESG-labelled products governed by clear eligibility criteria and product approval controls to prevent greenwashing. | Product | Quarterly | EV-008 | Not Started | 2026-05-15
CBUAE-009 | Governance | Art 2 | 2.7 | Customer due diligence and ongoing monitoring for green/ESG products (use-of-proceeds / KPIs / terms). | Compliance | Ongoing | EV-009 | In Progress | 2026-06-14
CBUAE-010 | Strategy | Art 3 | 3.1 | Assess climate-risk impacts on business environment, business model and activities across short/medium/long horizons. | Strategy | Annual | EV-010 | In Progress | 2026-07-14
CBUAE-011 | Strategy | Art 3 | 3.2 | Define and cascade mitigation actions and strategic adjustments into execution plans (products, markets, operations, IT, resourcing). | COO | Annual | EV-011 | Not Started | 2026-08-13
CBUAE-012 | ERM | Art 4 | 4.1 | Integrate climate risk into risk taxonomy and ERM framework (identification, measurement, control, reporting, mitigation). | ERM | Annual | EV-012 | In Progress | 2026-03-16
CBUAE-013 | ERM | Art 4 | 4.2 | Establish climate data management framework compliant with UAE data protection laws. | Data Office | Annual | EV-013 | Not Started | 2026-04-15
CBUAE-014 | ERM | Art 4 | 4.3 | Define climate metrics/KRIs linking physical/transition/liability drivers to existing risk categories. | Risk Analytics | Quarterly | EV-014 | In Progress | 2026-05-15
CBUAE-015 | ERM | Art 4 | 4.4 | Internal reporting system provides relevant, accurate, timely climate-risk information to Board and senior management. | Risk Reporting | Monthly | EV-015 | In Progress | 2026-06-14
CBUAE-016 | ERM | Art 4 | 4.5 | Set climate risk limits consistent with risk appetite and define breach escalation procedures. | CRO | Quarterly | EV-016 | Not Started | 2026-07-14
CBUAE-017 | ERM | Art 4 | 4.6 | Implement mitigation tools addressing impacts on business model, capital and liquidity over multiple horizons. | Treasury | Quarterly | EV-017 | In Progress | 2026-08-13
CBUAE-018 | Credit/Underwriting | Art 4 | 4.7 | Embed climate considerations in credit, investment and underwriting policies and lifecycle processes (origination to monitoring). | Credit Risk | Quarterly | EV-018 | In Progress | 2026-03-16
CBUAE-019 | Credit/Underwriting | Art 4 | 4.7 | Customer-level assessment covers collateral values, cashflows, profitability, project economics and transition plans; considers physical/transition/liability risks. | Credit Risk | Ongoing | EV-019 | Not Started | 2026-04-15
CBUAE-020 | Credit/Underwriting | Art 4 | 4.7 | Portfolio exposure mapping by geography/sector/concentration (including collateral where relevant). | Risk Analytics | Quarterly | EV-020 | In Progress | 2026-05-15
CBUAE-021 | Credit/Underwriting | Art 4 | 4.7 | External climate ratings use controlled: suitability review, limitations documented, and adjustments justified where applied. | Model Risk | Annual | EV-021 | Not Started | 2026-06-14
CBUAE-022 | Credit/Underwriting | Art 4 | 4.7 | Develop in-house climate scoring overlay combining quantitative and qualitative factors. | Model Risk | Annual | EV-022 | Blocked | 2026-07-14
CBUAE-023 | Market Risk | Art 4 | 4.8 | Assess market positions for climate exposure; consider repricing risk from sentiment, technology and policy shifts. | Market Risk | Monthly | EV-023 | In Progress | 2026-08-13
CBUAE-024 | Market Risk | Art 4 | 4.8 | Use stress/sensitivity analysis for climate-driven shocks and non-linear effects in valuations. | Market Risk | Quarterly | EV-024 | Not Started | 2026-03-16
CBUAE-025 | Operational/BCP | Art 4 | 4.9 | Assess physical climate risk impacts on business continuity, outsourcing and critical functions; update BCP accordingly. | Operational Risk | Annual | EV-025 | In Progress | 2026-04-15
CBUAE-026 | Liquidity Risk | Art 4 | 4.10 | Assess climate drivers for liquidity/funding under normal and stress conditions; integrate into liquidity planning horizons. | Treasury | Quarterly | EV-026 | Not Started | 2026-05-15
CBUAE-027 | Scenario Analysis | Art 4 | 4.11 | Maintain internal capability to perform climate scenario analysis at least annually. | Risk Analytics | Annual | EV-027 | In Progress | 2026-06-14
CBUAE-028 | Scenario Analysis | Art 4 | 4.11 | Scenarios cover physical/transition/liability risk, multi-horizon (S/M/L) and include plausible and severe pathways. | Risk Analytics | Annual | EV-028 | Not Started | 2026-07-14
CBUAE-029 | Scenario Analysis | Art 4 | 4.11 | Document scenario rationale, assumptions, variables, results, management actions; compare against baseline. | Risk Analytics | Annual | EV-029 | Not Started | 2026-08-13
CBUAE-030 | Scenario Analysis | Art 4 | 4.11 | Use outputs to update risk framework adequacy and define mitigation actions; feed into capital and liquidity planning. | CRO | Annual | EV-030 | In Progress | 2026-03-16
CBUAE-031 | Capital/Solvency | Art 5 | 5.1 | Evaluate capital and solvency impacts of climate risks over planning horizons. | Finance | Annual | EV-031 | In Progress | 2026-04-15
CBUAE-032 | Capital/Solvency | Art 5 | 5.2 | Integrate climate risks into ICAAP (banks) or ORSA (insurers) with documented results and actions. | Finance | Annual | EV-032 | Not Started | 2026-05-15
CBUAE-033 | Compliance | Art 6 | 6.1 | Implement compliance monitoring and testing (2LoD + Internal Audit) for climate-risk requirements. | Compliance | Semi-Annual | EV-033 | In Progress | 2026-06-14
CBUAE-034 | Remediation | Art 6 | 6.2 | Prepare remediation plan for any gaps with rationale, milestones, owners and progress reporting to CBUAE as needed. | Compliance | As Needed | EV-034 | Not Started | 2026-07-14
CBUAE-035 | Supervisory/Enforcement | Art 7-8 | 7.1 | Supervisory readiness: maintain evidence pack; understand potential supervisory actions/sanctions for non-compliance. | Compliance | Quarterly | EV-035 | In Progress | 2026-08-13

## Remediation_Plan
Action_ID | Req_ID | Requirement (auto) | Gap / Issue | Action | Owner | Due_Date | Action_Status | Dependency | Notes
A-001 | CBUAE-006 | Committee mandates updated (Risk/Audit/Remuneration) to include climate responsibilities and escalation routes. | Risk/Audit/RemCo ToR missing climate responsibilities | Draft amendments + route for Board approval | Board Secretariat | 2026-04-15 | In Progress | CBUAE-003
A-002 | CBUAE-008 | Green/ESG-labelled products governed by clear eligibility criteria and product approval controls to prevent greenwashing. | No documented eligibility criteria; greenwashing risk | Publish eligibility criteria + product approval checklist | Product | 2026-04-30 | Not Started | CBUAE-003
A-003 | CBUAE-013 | Establish climate data management framework compliant with UAE data protection laws. | Data governance not finalized | Define data model, lineage, access controls, retention | Data Office | 2026-05-15 | Not Started | CBUAE-012
A-004 | CBUAE-016 | Set climate risk limits consistent with risk appetite and define breach escalation procedures. | Limits not defined | Propose limits per sector/geography + breach workflow | CRO | 2026-04-20 | Not Started | CBUAE-005
A-005 | CBUAE-019 | Customer-level assessment covers collateral values, cashflows, profitability, project economics and transition plans; considers physical/transition/liability risks. | Credit file lacks climate fields | Add climate sections to credit memo + training | Credit Risk | 2026-04-10 | In Progress | CBUAE-018
A-006 | CBUAE-021 | External climate ratings use controlled: suitability review, limitations documented, and adjustments justified where applied. | No suitability policy | Implement vendor due diligence + model risk review | Model Risk | 2026-04-25 | Blocked | CBUAE-013 | Vendor contract pending
A-007 | CBUAE-024 | Use stress/sensitivity analysis for climate-driven shocks and non-linear effects in valuations. | No climate stress scenarios for trading book | Add climate shock factors into sensitivity tests | Market Risk | 2026-05-05 | Not Started | CBUAE-023
A-008 | CBUAE-026 | Assess climate drivers for liquidity/funding under normal and stress conditions; integrate into liquidity planning horizons. | ILAAP not updated | Incorporate climate drivers into liquidity stress tests | Treasury | 2026-05-10 | Not Started | CBUAE-030
A-009 | CBUAE-028 | Scenarios cover physical/transition/liability risk, multi-horizon (S/M/L) and include plausible and severe pathways. | Severe + multi-horizon set not defined | Select 3 pathways; define variables and narratives | Risk Analytics | 2026-04-05 | In Progress | CBUAE-027
A-010 | CBUAE-032 | Integrate climate risks into ICAAP (banks) or ORSA (insurers) with documented results and actions. | Climate not embedded in ICAAP module | Update ICAAP/ORSA sections + governance sign-off | Finance | 2026-05-20 | Not Started | CBUAE-031

## Evidence_Register
Evidence_ID | Evidence_Type | Artifact / Document Name | Owner | Location / Link (text) | Last_Updated | Related_Req_Count | Notes
EV-001 | Policy | Regulation Applicability Memo | Compliance | SharePoint/Compliance/CBUAE/Applicability | 2026-02-10 | 1
EV-002 | Methodology | Proportionality Statement | CRO | SharePoint/Risk/Climate/Proportionality | 2026-02-12 | 1 | Draft under review
EV-003 | Minutes | Board Approval Minutes (Climate Governance) | Board Secretariat | Board Portal/Minutes/2026-Q1 | 2026-02-05 | 1
EV-004 | Training | Board Climate Training Plan & Attendance Log | HR / L&D | LMS/Board/Climate-Training | 2026-02-15 | 1
EV-005 | Dashboard | Board Climate Risk Dashboard v1 | Risk Reporting | PowerBI/Board/ClimateRisk | 2026-02-20 | 1 | Monthly pack
EV-006 | Charter | Committee ToR Update Draft | Board Secretariat | Board Portal/Charters/Drafts | 2026-02-18 | 1 | Pending approval
EV-010 | Assessment | Business Model Climate Impact Assessment | Strategy | SharePoint/Strategy/Climate/Assessment | 2026-02-22 | 1
EV-012 | Framework | ERM Climate Integration Paper | ERM | SharePoint/Risk/ERM/Climate | 2026-02-19 | 1
EV-027 | Capability | Scenario Analysis Capability Note | Risk Analytics | SharePoint/Risk/Climate/Scenarios | 2026-02-14 | 1
EV-031 | Working Paper | Capital Impact Assessment (Climate) | Finance | SharePoint/Finance/ICAAP/Climate | 2026-02-21 | 1

## Metrics_KRIs
Metric_ID | Risk_Type | Metric / KRI Definition | Unit | Data_Source | Owner | Frequency | Data_Available (Y/N) | Notes
KRI-01 | Physical | % of collateral value in high flood-risk zones (top 20% hazard percentile) | % | Geo-risk vendor | Risk Analytics | Quarterly | Y | Pilot for mortgage book
KRI-02 | Transition | Exposure to carbon-intensive sectors as % of total portfolio | % | Core banking + SIC | Credit Risk | Monthly | Y | Uses sector taxonomy mapping
KRI-03 | Transition | Financed emissions (Scope 1+2) coverage rate for corporate clients | % | Client ESG data | Risk Analytics | Quarterly | N | Awaiting data contracts
KRI-04 | Liability | Number of climate-related litigation/watchlist cases involving clients | count | Legal watchlist | Compliance | Quarterly | Y | Manual tracking
KRI-05 | Physical | Operational downtime hours due to extreme weather events | hours | BCP logs | Operational Risk | Monthly | Y
KRI-06 | Transition | Green asset ratio (eligible green exposures / total) | % | Product system | Product | Monthly | N | Eligibility criteria pending