## Snapshot
This template is a practical compliance toolkit that converts the key obligations in the Federal Decree-Law No. (6) of 2025 Regarding the Central Bank, Regulation of Financial Institutions and Activities,and Insurance Business into three operational checklists for financial institutions: (1) Licensing and permitted activities (including controls to prevent unlicensed activity or promotion), (2) Governance and authorized individuals (board/senior appointments, fit-and-proper evidence, approvals, and accountability), and (3) Ongoing supervision, reporting, and inspection readiness (regulatory calendar, evidence packs, related-party exposures, and supervisory response processes). Each checklist is structured like a controls tracker with clear owners, frequency, due dates, evidence/artefacts, and status so teams can manage implementation and demonstrate compliance. Each module also has its own dashboard that automatically summarizes progress, overdue items, and status distribution for management reporting, and a Definitions tab standardizes terms and status meanings so the workbook can be used consistently across compliance, risk, legal, and internal audit.

## Checklist 1 - Licensing
Checklist 1: Licensing, Permitted Activities, and Promotion Controls
Use this checklist to confirm the institution operates only within licensed scope and maintains controls for promotion and emerging-technology delivery of Licensed Financial Activities.
Last updated: | 2026-03-01
Checklist owner: | Compliance / Regulatory Affairs
Control ID | Domain | Requirement / Control statement | Reference (Article/Item) in Federal Decree-Law No. (6) of 2025 | Applicability | Owner function | Control type | Testing method | Evidence / artefact | Frequency | Priority | Due date | Last reviewed | Status | RAG | Next action / notes | Evidence link
LIC-001 | Licensing perimeter | Maintain a current register of all Licensed Financial Activities carried on by the institution and ensure each activity is covered by an active CBUAE license (including branch/affiliate scope where relevant). | Art. 60(1)-(2), 60(6) | All Licensed Financial Institutions | Compliance | Preventive | Both | License certificates; activity register; product catalog mapping | Quarterly | High | 2026-04-30 | 2026-01-30 | Implemented | Green | Implemented; maintain licensing perimeter evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-001
LIC-002 | Marketing & promotion | Operate a mandatory pre-approval process for any promotion/communication inviting customers to enter into transactions for Licensed Financial Activities or financial products; keep evidence of approvals and version control. | Art. 60(3) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Marketing approval workflow; samples; approval logs | Continuous | High | 2026-03-31 | 2026-01-29 | Implemented | Green | Implemented; maintain marketing & promotion evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-002
LIC-003 | Licensing perimeter | Implement controls to prevent any staff/agent/partner from representing the institution as a Licensed Financial Institution where it is not licensed (including on websites, apps, social media, and partner channels). | Art. 60(7) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Branding guidelines; monitoring reports; takedown records | Monthly | High | 2026-03-26 | 2026-01-28 | Implemented | Green | Implemented; maintain licensing perimeter evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-003
LIC-004 | Scope of license | Ensure business operations remain within the scope of the granted license; maintain a documented ‘scope guardrail’ for new products and distribution channels. | Art. 60(6) | All Licensed Financial Institutions | Business / Product | Preventive | Both | Scope guardrail document; product governance minutes | Continuous | High | 2026-03-31 | 2026-01-27 | Implemented | Green | Implemented; maintain scope of license evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-004
LIC-005 | Exemptions management | If relying on any exemption issued by the Board of Directors, maintain documented basis, scope, conditions, and expiry; monitor continued eligibility. | Art. 60(5) | All Licensed Financial Institutions | Legal | Preventive | Design effectiveness | Exemption letter; legal memo; monitoring log | Quarterly | Medium | 2026-04-30 | 2026-01-26 | Implemented | Green | Implemented; maintain exemptions management evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-005
LIC-006 | Activity taxonomy | Map each product/service to the Central Bank’s Licensed Financial Activities taxonomy (e.g., deposits, credit facilities, funding facilities incl. Shari’ah-compliant, open finance, money transfer, virtual-asset payments, stored value/retail payments/digital money, arranging/promoting, principal trading, insurance). | Art. 61(1)(b)-(j) | All Licensed Financial Institutions | Compliance | Preventive | Design effectiveness | Activity mapping matrix; product sheets | Quarterly | High | 2026-04-30 | 2026-01-25 | Implemented | Green | Implemented; maintain activity taxonomy evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-006
LIC-007 | Change control | Maintain a regulatory change process to track any additions/deletions/amendments to the Licensed Financial Activities list made by the Board of Directors and assess impact on products and licensing needs. | Art. 61(2) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Reg change log; impact assessments | Monthly | High | 2026-03-26 | 2026-01-24 | Implemented | Green | Implemented; maintain change control evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-007
LIC-008 | Multi-regulator activities | Where the institution intends to carry on activities licensed by other regulators (inside/outside State or in Financial Free Zones) that are not in Art. 61(1), obtain Central Bank approval before applying to the other regulator. | Art. 61(3) | All Licensed Financial Institutions | Legal | Preventive | Operating effectiveness | Approval request; CBUAE approval; regulator correspondence | Event-driven | High | 2026-04-15 | 2026-01-23 | Implemented | Green | Implemented; maintain multi-regulator activities evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-008
LIC-009 | Emerging technologies perimeter | Maintain a documented assessment confirming that any offering/issuing/facilitating of Licensed Financial Activities using any medium/technology/form falls under CBUAE licensing and oversight; include third-party platforms and indirect facilitation. | Art. 62 (chapeau) | All Licensed Financial Institutions | Compliance | Preventive | Design effectiveness | Perimeter assessment template; completed assessments | Event-driven | High | 2026-04-15 | 2026-01-22 | Implemented | Green | Implemented; maintain emerging technologies perimeter evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/LIC/LIC-009
LIC-010 | Virtual assets/DeFi | If using virtual asset payment tokens, DeFi, or other emerging technology in connection with Licensed Financial Activities, ensure the activity is treated as within licensing scope and covered by approved policies and controls. | Art. 62(1) | All Licensed Financial Institutions | Compliance / IT | Preventive | Both | Technology risk assessment; approved policies; architectural diagrams | Event-driven | High |  |  | Not Applicable | Grey | Not applicable for current business model/products; reassess annually or upon launch of relevant activity. | https://example.com/compliance/CBUAE/LIC/LIC-010
LIC-011 | Platforms/dApps/protocols | If offering/operating platforms, dApps, protocols, or infrastructure that enables financial services (payments, credit, deposits, FX, remittances, investment services), ensure appropriate licensing analysis and oversight controls exist. | Art. 62(2) | All Licensed Financial Institutions | IT/Security | Preventive | Both | Platform governance; vendor due diligence; control design | Event-driven | High | 2026-04-15 | 2026-02-19 | Monitoring | Amber | Monitoring; refresh platforms/dapps/protocols evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/LIC/LIC-011
LIC-012 | Licensing applications | Maintain a documented licensing application process for new licenses or extension of scope, including internal approvals and completeness checks against CBUAE requirements. | Art. 63(1) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Licensing SOP; submission checklist; approvals | Event-driven | High | 2026-04-15 | 2026-02-18 | Monitoring | Amber | Monitoring; refresh licensing applications evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/LIC/LIC-012
LIC-013 | Fit and proper | Ensure licensing submissions evidence fit and proper criteria for relevant persons (owners, board, senior management as required), with documented screening and attestations. | Art. 63(2)(a) | All Licensed Financial Institutions | HR / Compliance | Preventive | Both | Fit & proper packs; screening results | Event-driven | High | 2026-04-15 | 2026-02-17 | Monitoring | Amber | Monitoring; refresh fit and proper evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/LIC/LIC-013
LIC-014 | Capital adequacy (licensing) | Evidence minimum capital requirements and sources of funds for licensing and scope extensions; retain supporting financial statements and confirmations. | Art. 63(2)(b) | All Licensed Financial Institutions | Finance | Preventive | Design effectiveness | Capital calculations; audited FS; confirmations | Event-driven | High | 2026-04-15 | 2026-02-16 | Monitoring | Amber | Monitoring; refresh capital adequacy (licensing) evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/LIC/LIC-014
LIC-015 | Resources | Demonstrate adequate resources (staffing, systems, expertise, outsourcing arrangements) to carry on each Licensed Financial Activity; maintain resourcing model and training plan. | Art. 63(2)(c) | All Licensed Financial Institutions | Operations | Preventive | Design effectiveness | Org charts; hiring plan; training records | Annual | Medium | 2026-08-28 | 2026-02-15 | Monitoring | Amber | Monitoring; refresh resources evidence and reconfirm operating effectiveness by 2026-08-28. | https://example.com/compliance/CBUAE/LIC/LIC-015
LIC-016 | Control & monitoring systems | Document and maintain control and monitoring systems for each Licensed Financial Activity (including operational, compliance, and technology controls) and update them when products change. | Art. 63(2)(d) | All Licensed Financial Institutions | Risk Management | Preventive | Both | Control library; monitoring reports; issue logs | Quarterly | High | 2026-04-30 | 2026-02-14 | Monitoring | Amber | Monitoring; refresh control & monitoring systems evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/LIC/LIC-016
LIC-017 | CBUAE additional requirements | Track and evidence fulfillment of any additional requirements/conditions imposed by the Central Bank during licensing review; assign accountable owners and deadlines. | Art. 63(3) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Requirement tracker; correspondence; closure evidence | Event-driven | High | 2026-03-28 | 2026-02-22 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/LIC/LIC-017
LIC-018 | Regulatory timelines | Maintain an internal tracker for the 60-working-day decision period after meeting all licensing conditions; document any information requests and when conditions were satisfied. | Art. 64(1)-(2) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Timeline tracker; submission receipts; responses | Event-driven | Medium | 2026-03-28 | 2026-02-21 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/LIC/LIC-018
LIC-019 | Application rejection handling | If licensing/scope application is rejected, document the basis and business response plan, including market-entry alternatives and remediation actions. | Art. 64(3) | All Licensed Financial Institutions | Business / Legal | Corrective | Design effectiveness | Board paper; remediation plan | Event-driven | Medium | 2026-03-28 | 2026-02-20 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/LIC/LIC-019
LIC-020 | Recordkeeping | Maintain centralized records of all licensing approvals, conditions, correspondence, and scope changes; ensure retention and accessibility for examination. | Art. 133 (exam access to records) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Repository index; retention policy; access logs | Continuous | High | 2026-03-19 | 2026-02-19 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-19. | https://example.com/compliance/CBUAE/LIC/LIC-020
LIC-021 | Outsourcing/agents | Ensure any third parties involved in promotion or facilitation of Licensed Financial Activities are contractually bound to follow your licensing perimeter and promotion controls; monitor their compliance. | Art. 60(3) (promotion controls) | All Licensed Financial Institutions | Procurement / Compliance | Preventive | Operating effectiveness | Contracts; monitoring results; audit reports | Quarterly | High | 2026-04-06 | 2026-02-18 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-04-06. | https://example.com/compliance/CBUAE/LIC/LIC-021
LIC-022 | Product governance | Implement a ‘new product approval’ gate requiring: (i) licensing perimeter assessment, (ii) compliance review, (iii) customer risk disclosures, and (iv) operational readiness confirmation. | Art. 60(6), 62 (tech perimeter) | All Licensed Financial Institutions | Business / Product | Preventive | Both | NPA template; approvals; launch checklist | Event-driven | High | 2026-03-28 | 2026-02-24 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/LIC/LIC-022
LIC-023 | Listed institutions | If listed in State’s financial markets, ensure governance minimum requirements set by the concerned regulatory authority are integrated into your licensing and product governance processes. | Art. 130(1) proviso | All Licensed Financial Institutions | Board Secretariat | Preventive | Design effectiveness | Governance mapping; policy references | Annual | Medium | 2026-06-17 | 2026-02-23 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-06-17. | https://example.com/compliance/CBUAE/LIC/LIC-023
LIC-024 | Policy alignment | Incorporate Board of Directors’ regulations/standards/directives relating to prohibition of unlicensed activities into internal policies and training material; evidence periodic updates. | Art. 60(4) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Policy updates; training updates; governance sign-offs | Quarterly | Medium | 2026-04-18 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
LIC-025 | Periodic attestation | Perform a semi-annual self-assessment attestation that all activities remain within licensed scope and that promotion controls are operating effectively; escalate exceptions. | Art. 60(6), 60(3) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Self-assessment report; exception log; remediation actions | Semi-Annual | Medium | 2026-02-22 |  | Not Started | Red | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
LIC-026 | Product documentation | Ensure product terms, disclosures, and customer communications accurately describe the regulated service and do not imply services outside licensing scope. | Art. 60(6)-(7) | All Licensed Financial Institutions | Legal / Compliance | Preventive | Design effectiveness | Product T&Cs; disclosure templates; legal reviews | Event-driven | Medium | 2026-04-06 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
LIC-027 | Partner/channel oversight | Maintain monitoring of digital channels (web/app) and partner channels to identify unauthorized promotion of Licensed Financial Activities; execute takedown and remediation workflows. | Art. 60(3) | All Licensed Financial Institutions | Marketing / Compliance | Detective | Operating effectiveness | Monitoring reports; takedown tickets; partner notices | Monthly | High | 2026-03-21 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
LIC-028 | Internal assurance | Include licensing perimeter and promotion controls in the internal audit plan; track findings and remediation to closure. | Art. 114(2) (proper conduct) | All Licensed Financial Institutions | Internal Audit | Detective | Operating effectiveness | Audit reports; action plans; closure evidence | Annual | Medium | 2026-02-15 |  | Not Started | Red | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
LIC-029 | Third-party due diligence | Perform due diligence on technology providers/platform operators used to facilitate Licensed Financial Activities (including DeFi-related infrastructure) and document governance, security, and operational controls. | Art. 62(2) + Art. 63(2)(c)-(d) | All Licensed Financial Institutions | Procurement / IT | Preventive | Both | Vendor DD reports; risk assessments; contracts | Annual | High | 2026-02-08 | 2026-02-06 | Blocked | Red | Blocked due to dependency (system/process/vendor); escalate and agree remediation plan; interim workaround required. | https://example.com/compliance/CBUAE/LIC/LIC-029
LIC-030 | Issue management | Operate an incident and breach management process for suspected unlicensed activity or non-compliant promotion, including immediate cessation, root cause analysis, and regulator engagement where needed. | Art. 60(1)-(3) + Art. 114 | All Licensed Financial Institutions | Compliance | Corrective | Design effectiveness | Incident SOP; incident logs; RCA reports | Event-driven | High | 2026-02-08 | 2026-02-05 | Blocked | Red | Blocked due to dependency (system/process/vendor); escalate and agree remediation plan; interim workaround required. | https://example.com/compliance/CBUAE/LIC/LIC-030
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Formulas:
RAG = IF([Status]="Implemented","Green",IF([Status]="Not Applicable","Grey",IF(AND([Due date]<>"",[Due date]<TODAY()),"Red",IF([Status]="Blocked","Red",IF([Status]="In Progress","Amber",IF([Status]="Not Started","Amber","Amber"))))))

## Dashboard 1 - Licensing
Dashboard 1: Licensing & Activity Scope
Linked checklist: Checklist 1 - Licensing
KPI | Value
Total controls | 30
Applicable controls | 29
Implemented | 9
In progress | 7
Not started | 5
Monitoring | 6
Blocked | 2
Overdue (due date passed) | 4
% complete (Implemented / Applicable) | 31.03%
Status | Count
Not Started | 5
In Progress | 7
Implemented | 9
Monitoring | 6
Blocked | 2
Not Applicable | 1
Owner function | Count
Compliance | 13
Legal | 2
Board Secretariat | 1
Risk Management | 1
Operations | 1
IT/Security | 1
Finance | 1
Internal Audit | 1

## Checklist 2 - Governance
Checklist 2: Governance, Board Approvals, and Authorized Individuals
Use this checklist to operationalize governance obligations, prior approval gates for board/Authorized Individuals, and core integrity controls (confidentiality and conflicts).
Last updated: | 2026-03-01
Checklist owner: | Compliance / Regulatory Affairs
Control ID | Domain | Requirement / Control statement | Reference (Article/Item) in Federal Decree-Law No. (6) of 2025 | Applicability | Owner function | Control type | Testing method | Evidence / artefact | Frequency | Priority | Due date | Last reviewed | Status | RAG | Next action / notes | Evidence link
GOV-001 | Governance framework | Adopt and maintain a corporate governance framework aligned to the Central Bank’s governance framework for Licensed Financial Institutions, including board structures, committees, and delegated authorities. | Art. 130(1) | All Licensed Financial Institutions | Board Secretariat | Preventive | Design effectiveness | Governance charter; committee ToR; delegation matrix | Annual | High | 2026-08-28 | 2026-01-30 | Implemented | Green | Implemented; maintain governance framework evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-001
GOV-002 | Board composition | Maintain documented criteria for board member eligibility meeting CBUAE conditions; perform pre-appointment diligence and ongoing annual attestations. | Art. 130(1) | All Licensed Financial Institutions | Board Secretariat | Preventive | Both | Board eligibility policy; attestations; assessments | Annual | High | 2026-08-28 | 2026-01-29 | Implemented | Green | Implemented; maintain board composition evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-002
GOV-003 | Prior approval (board) | Obtain Central Bank prior approval for nomination/appointment/renewal of any board member; maintain an approvals tracker with expiry/renewal dates. | Art. 130(2) | All Licensed Financial Institutions | Board Secretariat | Preventive | Operating effectiveness | CBUAE submissions; approvals; tracker | Event-driven | High | 2026-04-15 | 2026-01-28 | Implemented | Green | Implemented; maintain prior approval (board) evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-003
GOV-004 | Prior approval (authorized individuals) | Obtain Central Bank prior approval for appointment/renewal of employment contracts of Authorized Individuals; maintain a register of Authorized Individuals and approvals. | Art. 130(2) | All Licensed Financial Institutions | HR / Compliance | Preventive | Operating effectiveness | Authorized Individuals register; approvals; contract files | Event-driven | High | 2026-04-15 | 2026-01-27 | Implemented | Green | Implemented; maintain prior approval (authorized individuals) evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-004
GOV-005 | Rejection response | If CBUAE rejects a nomination/appointment/renewal (board or Authorized Individual), document response actions, succession plan activation, and communications controls. | Art. 130(3) | All Licensed Financial Institutions | Board Secretariat | Corrective | Design effectiveness | Succession plan; board minutes; action log | Event-driven | High | 2026-04-15 | 2026-01-26 | Implemented | Green | Implemented; maintain rejection response evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-005
GOV-006 | Rulebook monitoring | Operate a formal regulatory change management process that monitors the CBUAE Rulebook (and updates on CBUAE website), assesses impact, assigns actions, and tracks closure. | Art. 131 | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Reg change log; impact assessments; closure evidence | Monthly | High | 2026-03-26 | 2026-01-25 | Implemented | Green | Implemented; maintain rulebook monitoring evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-006
GOV-007 | Transitional periods | When new regulations/decisions/circulars are issued, identify and document applicable transitional periods set by CBUAE and execute a reconciliation plan to meet requirements by deadline. | Art. 132 | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Transition plan; project plan; sign-offs | Event-driven | High | 2026-04-15 | 2026-01-24 | Implemented | Green | Implemented; maintain transitional periods evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-007
GOV-008 | Confidentiality | Maintain a confidentiality policy and controls for handling confidential information (including classification, access controls, secure sharing, and retention), and enforce continued confidentiality after role termination. | Art. 26 | All Licensed Financial Institutions | Legal / Compliance | Preventive | Both | Confidentiality policy; access logs; NDAs | Annual | High | 2026-08-28 | 2026-01-23 | Implemented | Green | Implemented; maintain confidentiality evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-008
GOV-009 | Conflicts of interest | Operate a conflicts-of-interest declaration and recusal process for board members and relevant staff; ensure interests are disclosed and voting/participation controls are enforced. | Art. 27 | All Licensed Financial Institutions | Board Secretariat | Preventive | Operating effectiveness | COI register; meeting minutes; recusals | Quarterly | High | 2026-04-30 | 2026-01-22 | Implemented | Green | Implemented; maintain conflicts of interest evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-009
GOV-010 | Code of conduct | Maintain a code of conduct aligned with governance rules issued by the Board of Directors (CBUAE) and ensure staff training and attestations are completed. | Art. 27(1) (code of conduct & governance rules) | All Licensed Financial Institutions | HR / Compliance | Preventive | Operating effectiveness | Code of conduct; training logs; attestations | Annual | Medium | 2026-08-28 | 2026-01-21 | Implemented | Green | Implemented; maintain code of conduct evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/GOV/GOV-010
GOV-011 | Designated functions | Identify all ‘Designated Functions’/key roles and ensure individuals occupying them meet fit-and-proper expectations and are not subject to CBUAE prohibition. | Art. 112 | All Licensed Financial Institutions | HR / Compliance | Preventive | Both | Role map; fit & proper files; CBUAE correspondence | Semi-Annual | High | 2026-04-15 | 2026-02-19 | Monitoring | Amber | Monitoring; refresh designated functions evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/GOV/GOV-011
GOV-012 | Governance documentation | Maintain board/committee calendars, agendas, minutes, and decision logs with appropriate retention and confidentiality controls; ensure decisions are traceable to delegated authorities. | Art. 133 (examination) + Art. 26 (confidentiality) | All Licensed Financial Institutions | Board Secretariat | Detective | Operating effectiveness | Minutes; decision register; retention schedule | Quarterly | High | 2026-04-30 | 2026-02-18 | Monitoring | Amber | Monitoring; refresh governance documentation evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/GOV/GOV-012
GOV-013 | Subsidiary governance | Ensure group and subsidiary governance arrangements do not impede CBUAE consolidated supervision; document escalation and cooperation mechanisms with parent and subsidiaries. | Art. 127-128 (consolidated supervision) | All Licensed Financial Institutions | Risk Management | Preventive | Design effectiveness | Group governance policy; org charts; MoUs | Annual | High | 2026-08-28 | 2026-02-17 | Monitoring | Amber | Monitoring; refresh subsidiary governance evidence and reconfirm operating effectiveness by 2026-08-28. | https://example.com/compliance/CBUAE/GOV/GOV-013
GOV-014 | Regulatory engagement | Maintain a regulated engagement protocol for communications with CBUAE (single point of contact, sign-off matrix, tracking of requests and commitments). | Art. 114 (compliance with instructions) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Engagement SOP; tracker; correspondence | Continuous | High | 2026-03-31 | 2026-02-16 | Monitoring | Amber | Monitoring; refresh regulatory engagement evidence and reconfirm operating effectiveness by 2026-03-31. | https://example.com/compliance/CBUAE/GOV/GOV-014
GOV-015 | Internal control ownership | Establish a control library mapped to decree-law obligations with clear owners, test plans, and remediation workflow; report key compliance metrics to senior management/board. | Art. 114(1)-(2) (instructions, proper conduct) | All Licensed Financial Institutions | Compliance | Detective | Both | Control library; compliance reports; remediation logs | Quarterly | High | 2026-04-30 | 2026-02-15 | Monitoring | Amber | Monitoring; refresh internal control ownership evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/GOV/GOV-015
GOV-016 | Training & competence | Provide governance and regulatory obligations training for board and Authorized Individuals (onboarding and refreshers), including promotion rules and technology perimeter. | Art. 60(3), 62, 130 | All Licensed Financial Institutions | HR / Compliance | Preventive | Operating effectiveness | Training curriculum; attendance; evaluations | Annual | Medium | 2026-08-28 | 2026-02-14 | Monitoring | Amber | Monitoring; refresh training & competence evidence and reconfirm operating effectiveness by 2026-08-28. | https://example.com/compliance/CBUAE/GOV/GOV-016
GOV-017 | Policy management | Implement version control and approval workflow for policies and procedures referenced in compliance obligations; ensure controlled distribution and acknowledgements. | Art. 114(1) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Policy register; approvals; acknowledgements | Quarterly | Medium | 2026-04-30 | 2026-02-13 | Monitoring | Amber | Monitoring; refresh policy management evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/GOV/GOV-017
GOV-018 | Third-party governance | Maintain governance oversight for material outsourced arrangements supporting Licensed Financial Activities, including approval, monitoring, and exit plans. | Art. 63(2)(c)-(d) (resources, monitoring) | All Licensed Financial Institutions | Operations | Preventive | Both | Outsourcing register; SLAs; monitoring reports | Quarterly | Medium | 2026-04-06 | 2026-02-21 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-04-06. | https://example.com/compliance/CBUAE/GOV/GOV-018
GOV-019 | Audit & assurance | Ensure independent assurance (internal audit/second line) reviews the effectiveness of governance and compliance controls and reports findings to the board/committee. | Art. 114(2) (proper conduct) | All Licensed Financial Institutions | Internal Audit | Detective | Operating effectiveness | Audit plan; reports; management action plans | Annual | High | 2026-06-17 | 2026-02-20 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-06-17. | https://example.com/compliance/CBUAE/GOV/GOV-019
GOV-020 | Board/committee effectiveness | Perform annual board and committee effectiveness review and document action plan addressing governance gaps against CBUAE governance framework. | Art. 130(1) | All Licensed Financial Institutions | Board Secretariat | Detective | Design effectiveness | Board evaluation report; action plan; follow-up | Annual | Medium | 2026-06-17 | 2026-02-19 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-06-17. | https://example.com/compliance/CBUAE/GOV/GOV-020
GOV-021 | Onboarding | Run formal onboarding for board members and Authorized Individuals covering key decree-law obligations (licensing perimeter, promotion, confidentiality, conflicts, reporting, examinations). | Art. 60, 26, 27, 114, 116, 133 | All Licensed Financial Institutions | Board Secretariat | Preventive | Operating effectiveness | Onboarding pack; attendance; acknowledgements | Event-driven | High | 2026-03-28 | 2026-02-18 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/GOV/GOV-021
GOV-022 | Succession planning | Maintain and test succession plans for board and Authorized Individuals roles to ensure continuity if approvals are delayed or rejected. | Art. 130(3) | All Licensed Financial Institutions | HR / Board Secretariat | Preventive | Design effectiveness | Succession plan; tabletop exercise results | Annual | Medium | 2026-06-17 | 2026-02-24 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-06-17. | https://example.com/compliance/CBUAE/GOV/GOV-022
GOV-023 | Information security governance | Ensure governance oversight of information security and confidentiality controls, including periodic reporting to relevant committee and follow-up of issues. | Art. 26 (confidentiality) | All Licensed Financial Institutions | IT/Security | Detective | Operating effectiveness | Committee reports; metrics; issue logs | Quarterly | High | 2026-04-06 | 2026-02-23 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-04-06. | https://example.com/compliance/CBUAE/GOV/GOV-023
GOV-024 | Whistleblowing / reporting | Maintain a confidential reporting mechanism for governance or compliance breaches and ensure investigations and remediation are tracked and reported appropriately. | Art. 114(2) (proper conduct) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Whistleblowing policy; case logs; closure evidence | Continuous | Medium | 2026-03-25 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
GOV-025 | Documented delegations | Maintain documented delegations of authority aligned to governance framework and ensure material regulatory matters are escalated to board/committees. | Art. 130(1) | All Licensed Financial Institutions | Board Secretariat | Preventive | Design effectiveness | DoA matrix; escalation protocol | Annual | Medium | 2026-02-22 |  | Not Started | Red | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
GOV-026 | Listed entity governance mapping | If listed, maintain a documented mapping between CBUAE governance framework and minimum corporate governance requirements of the relevant market regulator and evidence compliance with both. | Art. 130(1) proviso | All Licensed Financial Institutions | Legal / Board Secretariat | Detective | Design effectiveness | Mapping document; compliance attestations | Annual | Medium | 2026-07-23 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
GOV-027 | Regulatory commitments tracking | Track all commitments made to CBUAE (actions, deadlines, deliverables) and provide periodic status reports to senior management/board. | Art. 114(1)-(2) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Commitment tracker; status reports | Monthly | High | 2026-03-21 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
GOV-028 | Authorized Individuals lifecycle | Implement lifecycle controls for Authorized Individuals (role changes, interim appointments, departures) ensuring approvals/notifications are completed and access rights updated. | Art. 130(2) | All Licensed Financial Institutions | HR / IT | Preventive | Operating effectiveness | Role change workflow; access change tickets; approvals | Event-driven | High | 2026-02-08 | 2026-02-07 | Blocked | Red | Blocked due to dependency (system/process/vendor); escalate and agree remediation plan; interim workaround required. | https://example.com/compliance/CBUAE/GOV/GOV-028
GOV-029 | Governance policy library | Maintain a governance policy library (board charter, committee ToR, COI, confidentiality, fit & proper) with version control and periodic review schedule. | Art. 130(1), Art. 26, Art. 27 | All Licensed Financial Institutions | Board Secretariat | Detective | Operating effectiveness | Policy register; review records | Annual | Medium |  |  | Not Applicable | Grey | Not applicable for current business model/products; reassess annually or upon launch of relevant activity. | https://example.com/compliance/CBUAE/GOV/GOV-029
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Formulas:
RAG = IF([Status]="Implemented","Green",IF([Status]="Not Applicable","Grey",IF(AND([Due date]<>"",[Due date]<TODAY()),"Red",IF([Status]="Blocked","Red",IF([Status]="In Progress","Amber",IF([Status]="Not Started","Amber","Amber"))))))

## Dashboard 2 - Governance
Dashboard 2: Governance & Approvals
Linked checklist: Checklist 2 - Governance
KPI | Value
Total controls | 29
Applicable controls | 28
Implemented | 10
In progress | 6
Not started | 4
Monitoring | 7
Blocked | 1
Overdue (due date passed) | 2
% complete (Implemented / Applicable) | 35.71%
Status | Count
Not Started | 4
In Progress | 6
Implemented | 10
Monitoring | 7
Blocked | 1
Not Applicable | 1
Owner function | Count
Compliance | 7
Legal | 0
Board Secretariat | 10
Risk Management | 1
Operations | 1
IT/Security | 1
Finance | 0
Internal Audit | 1

## Checklist 3 - Supervision
Checklist 3: Ongoing Supervision, Reporting, Examination Readiness, and Customer Protection
Use this checklist to track ongoing compliance with CBUAE instructions, consolidated supervision readiness, regulatory reporting, examinations, and fraud/customer protection controls.
Last updated: | 2026-03-01
Checklist owner: | Compliance / Regulatory Affairs
Control ID | Domain | Requirement / Control statement | Reference (Article/Item) in Federal Decree-Law No. (6) of 2025 | Applicability | Owner function | Control type | Testing method | Evidence / artefact | Frequency | Priority | Due date | Last reviewed | Status | RAG | Next action / notes | Evidence link
SUP-001 | Compliance repository | Maintain an obligations register covering all applicable CBUAE regulations, rules, standards, circulars, directives and instructions; map each obligation to a control and owner. | Art. 114(1) | All Licensed Financial Institutions | Compliance | Detective | Both | Obligations register; control mapping | Quarterly | High | 2026-04-30 | 2026-01-30 | Implemented | Green | Implemented; maintain compliance repository evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-001
SUP-002 | Instruction handling | Operate an intake and execution process for CBUAE instructions/measures/actions (logging, assignment, deadlines, evidence of completion) to ensure proper conduct of business. | Art. 114(2) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Instruction tracker; closure evidence; governance updates | Continuous | High | 2026-03-31 | 2026-01-29 | Implemented | Green | Implemented; maintain instruction handling evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-002
SUP-003 | Related parties register | Maintain a complete related-parties register covering board members, controlling shareholders, group entities, and other specified persons; update on trigger events. | Art. 116(1) | All Licensed Financial Institutions | Risk Management | Preventive | Both | Related parties register; change logs | Monthly | High | 2026-03-26 | 2026-01-28 | Implemented | Green | Implemented; maintain related parties register evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-003
SUP-004 | Quarterly related-party statement | Prepare the quarterly statement of all credit and funding facilities to related parties in the CBUAE-specified form. | Art. 116(1) | All Licensed Financial Institutions | Finance / Risk | Detective | Operating effectiveness | Quarterly statement; source data; sign-offs | Quarterly | High | 2026-04-30 | 2026-01-27 | Implemented | Green | Implemented; maintain quarterly related-party statement evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-004
SUP-005 | Submission timeliness | Submit the related-party statement to CBUAE within 10 working days from end of each quarter (or as requested); maintain submission proof. | Art. 116(2) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Submission receipt; tracker; correspondence | Quarterly | High | 2026-04-30 | 2026-01-26 | Implemented | Green | Implemented; maintain submission timeliness evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-005
SUP-006 | CBUAE review outcomes | If CBUAE indicates exposures may harm depositors, implement remediation actions directed by CBUAE (e.g., reduce exposure, strengthen collateral) and document closure. | Art. 116(3) | All Licensed Financial Institutions | Risk Management | Corrective | Operating effectiveness | Remediation plan; action evidence; communications | Event-driven | High | 2026-04-15 | 2026-01-25 | Implemented | Green | Implemented; maintain cbuae review outcomes evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-006
SUP-007 | Consolidated supervision readiness | Maintain an up-to-date group structure chart and list of subsidiaries/owned companies; ensure ability to provide consolidated prudential information on request. | Art. 127 | All Licensed Financial Institutions | Risk Management | Preventive | Both | Group structure chart; consolidated reporting pack | Quarterly | High | 2026-04-30 | 2026-01-24 | Implemented | Green | Implemented; maintain consolidated supervision readiness evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-007
SUP-008 | Prudential directives compliance | Comply with prudential directives issued under consolidated supervision (e.g., capital, liquidity, large exposures, risk management expectations) and evidence monitoring. | Art. 128(1) | All Licensed Financial Institutions | Risk Management | Preventive | Operating effectiveness | Prudential KPI dashboards; limit monitoring; breach logs | Monthly | High | 2026-03-26 | 2026-01-23 | Implemented | Green | Implemented; maintain prudential directives compliance evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-008
SUP-009 | Reporting obligations | Maintain a reporting inventory and submission calendar for all prudential and other reports required by CBUAE; reconcile data sources and retain audit trails. | Art. 128(1) + Art. 133 | All Licensed Financial Institutions | Finance | Detective | Operating effectiveness | Reporting calendar; reconciliations; data lineage | Monthly | High | 2026-03-26 | 2026-01-22 | Implemented | Green | Implemented; maintain reporting obligations evidence; include in routine control testing and retain artefacts. | https://example.com/compliance/CBUAE/SUP/SUP-009
SUP-010 | Parent notification actions | If CBUAE notifies the parent company to take measures/refrain from activities for consolidated supervision, maintain a response plan and evidence execution. | Art. 128(5) | All Licensed Financial Institutions | Group Compliance | Corrective | Operating effectiveness | Parent response plan; board minutes; actions | Event-driven | High | 2026-04-15 | 2026-02-10 | Monitoring | Amber | Monitoring; refresh parent notification actions evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/SUP/SUP-010
SUP-011 | Operational limits monitoring | Monitor and comply with any operational limits set by CBUAE (e.g., funding under securities/discount/loans, lending to a single person, dealing in foreign govt/corporate securities). | Art. 129 | All Licensed Financial Institutions | Risk Management | Preventive | Operating effectiveness | Limit framework; monitoring reports; breaches | Daily | High | 2026-04-15 | 2026-02-19 | Monitoring | Amber | Monitoring; refresh operational limits monitoring evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/SUP/SUP-011
SUP-012 | Cessation approval | Do not cease or suspend operations (fully/partially) or cease Licensed Financial Activities without CBUAE approval; maintain a cessation playbook and approval evidence. | Art. 126 | All Licensed Financial Institutions | Legal | Preventive | Operating effectiveness | Cessation playbook; approval letters; board papers | Event-driven | High | 2026-04-15 | 2026-02-18 | Monitoring | Amber | Monitoring; refresh cessation approval evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/SUP/SUP-012
SUP-013 | M&A approval gates | For mergers/acquisitions, ensure compliance with CBUAE rules/conditions/instructions and maintain decision notices and grievance rights records where applicable. | Art. 125(2)-(3) | All Licensed Financial Institutions | Legal | Preventive | Operating effectiveness | M&A regulatory checklist; submissions; notices | Event-driven | Medium | 2026-04-15 | 2026-02-17 | Monitoring | Amber | Monitoring; refresh m&a approval gates evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/SUP/SUP-013
SUP-014 | Examination readiness | Maintain an examination readiness pack (policies, registers, licenses, prudential reports, audit trails) and a response protocol for CBUAE staff or authorized third parties. | Art. 133(1) | All Licensed Financial Institutions | Compliance | Preventive | Operating effectiveness | Exam pack index; response SOP; drills | Quarterly | High | 2026-04-30 | 2026-02-16 | Monitoring | Amber | Monitoring; refresh examination readiness evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/SUP/SUP-014
SUP-015 | Records access | Ensure records, systems, and data are accessible to examiners and preserved securely; define data owners and rapid retrieval SLAs. | Art. 133(1) | All Licensed Financial Institutions | IT/Security | Preventive | Operating effectiveness | Data retention policy; access procedures; retrieval metrics | Quarterly | High | 2026-04-30 | 2026-02-15 | Monitoring | Amber | Monitoring; refresh records access evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/SUP/SUP-015
SUP-016 | Fraud controls | Implement robust fraud prevention and detection mechanisms to protect customers against unauthorized transactions, social engineering, identity theft and other fraud. | Art. 149(1) | All Licensed Financial Institutions | IT/Security | Preventive | Operating effectiveness | Fraud strategy; monitoring; incident logs | Continuous | High | 2026-03-31 | 2026-02-14 | Monitoring | Amber | Monitoring; refresh fraud controls evidence and reconfirm operating effectiveness by 2026-03-31. | https://example.com/compliance/CBUAE/SUP/SUP-016
SUP-017 | Security standards | Align digital and traditional banking security controls to any minimum standards issued by CBUAE (authentication, transaction monitoring, reporting obligations for suspected fraud). | Art. 149(2) | All Licensed Financial Institutions | IT/Security | Preventive | Both | Security standards mapping; control testing results | Quarterly | High | 2026-04-30 | 2026-02-13 | Monitoring | Amber | Monitoring; refresh security standards evidence and reconfirm operating effectiveness by 2026-04-30. | https://example.com/compliance/CBUAE/SUP/SUP-017
SUP-018 | Customer notification | Promptly notify affected customers of security breaches or fraudulent incidents and take immediate corrective actions to mitigate damage; maintain templates and timelines. | Art. 149(3) | All Licensed Financial Institutions | Operations | Corrective | Operating effectiveness | Incident comms log; templates; post-incident reports | Event-driven | High | 2026-04-15 | 2026-02-12 | Monitoring | Amber | Monitoring; refresh customer notification evidence and reconfirm operating effectiveness by 2026-04-15. | https://example.com/compliance/CBUAE/SUP/SUP-018
SUP-019 | Data/report submission | Be able to submit data, reports, or relevant information (including transaction records) to CBUAE when required; maintain extraction and validation procedures. | Art. 149(4) + Art. 133 | All Licensed Financial Institutions | Finance / IT | Detective | Operating effectiveness | Data extraction SOP; QA checks; submission proofs | Event-driven | High | 2026-03-28 | 2026-02-20 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/SUP/SUP-019
SUP-020 | Public awareness | Support public awareness initiatives on banking/insurance services and financial products and their risks, per CBUAE controls; maintain evidence of communications campaigns. | Art. 148(10) | All Licensed Financial Institutions | Marketing / Compliance | Detective | Design effectiveness | Campaign materials; approvals; metrics | Annual | Low | 2026-06-17 | 2026-02-19 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-06-17. | https://example.com/compliance/CBUAE/SUP/SUP-020
SUP-021 | No compound interest | Ensure systems and product terms do not apply interest on accrued interest (compound interest) on customer facilities; evidence adherence to CBUAE rules/controls. | Art. 148(11) | All Licensed Financial Institutions | Finance / Operations | Preventive | Operating effectiveness | System configuration; product terms; testing evidence | Quarterly | High | 2026-04-06 | 2026-02-18 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-04-06. | https://example.com/compliance/CBUAE/SUP/SUP-021
SUP-022 | Sanctions awareness | Maintain a compliance escalation process that considers potential administrative/financial sanctions (including large fines and license revocation) for breaches; ensure timely remediation and board reporting. | Sanctions chapter (incl. fines up to AED 1bn; revocation) | All Licensed Financial Institutions | Compliance | Corrective | Design effectiveness | Incident management SOP; board reports; remediation tracker | Continuous | High | 2026-03-19 | 2026-02-24 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-19. | https://example.com/compliance/CBUAE/SUP/SUP-022
SUP-023 | Grievances & appeals | Maintain a documented process to lodge grievances/appeals to the Grievances and Appeals Committee where rights are provided in decision notices; track timelines and outcomes. | Decision notices include grievance rights (e.g., Art. 125(3), Art. 114(3)) | All Licensed Financial Institutions | Legal | Corrective | Design effectiveness | Grievance SOP; filings; outcomes log | Event-driven | Medium | 2026-03-28 | 2026-02-23 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-28. | https://example.com/compliance/CBUAE/SUP/SUP-023
SUP-024 | Decision notice tracking | Log all formal CBUAE decisions/notices received (content, reasons, effective date) and ensure dissemination to relevant owners; confirm actions completed by effective dates. | Decision notice content requirements (various articles) | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Notice register; distribution emails; closure evidence | Continuous | High | 2026-03-19 | 2026-02-22 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-19. | https://example.com/compliance/CBUAE/SUP/SUP-024
SUP-025 | Data quality controls | Operate data quality controls for regulatory reporting (reconciliations, validations, sign-offs, and lineage) to support examination and reporting obligations. | Art. 133 (examination) | All Licensed Financial Institutions | Finance | Detective | Operating effectiveness | Reconciliation packs; QC logs; sign-offs | Monthly | High | 2026-03-16 | 2026-02-21 | In Progress | Amber | In progress; complete procedure update + evidence pack; target completion by 2026-03-16. | https://example.com/compliance/CBUAE/SUP/SUP-025
SUP-026 | Group impediments removal | Assess and remediate any legal/operational impediments that would prevent effective consolidated supervision or information sharing across the group. | Art. 127-128 (consolidated supervision) | All Licensed Financial Institutions | Group Compliance | Corrective | Design effectiveness | Impediments assessment; remediation plan; legal opinions | Annual | High | 2026-07-23 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
SUP-027 | Cross-border coordination | Maintain coordination procedures for overseas branches/subsidiaries and Financial Free Zone entities to respond to CBUAE consolidated supervision and cooperate with relevant regulators. | Art. 134 (cooperation/coordination) | All Licensed Financial Institutions | Group Compliance | Preventive | Design effectiveness | Regulator coordination protocol; MoUs; meeting notes | Semi-Annual | Medium | 2026-04-06 |  | Not Started | Amber | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
SUP-028 | Incident reporting readiness | Maintain an incident management framework that can meet any CBUAE reporting obligations for fraud/security incidents, including evidence of timely escalation and customer protection steps. | Art. 149(2)-(3) | All Licensed Financial Institutions | IT/Security | Corrective | Operating effectiveness | Incident playbooks; SLA metrics; incident logs | Continuous | High | 2026-02-15 |  | Not Started | Red | Not started; perform quick gap assessment and assign accountable owner; draft implementation plan.
SUP-029 | Customer awareness controls | Maintain customer communications governance for public awareness initiatives and risk disclosures, ensuring materials follow CBUAE controls and are approved by compliance. | Art. 148(10) | All Licensed Financial Institutions | Marketing / Compliance | Preventive | Operating effectiveness | Comms governance SOP; approval logs | Annual | Low | 2026-02-08 | 2026-02-06 | Blocked | Red | Blocked due to dependency (system/process/vendor); escalate and agree remediation plan; interim workaround required. | https://example.com/compliance/CBUAE/SUP/SUP-029
SUP-030 | Testing and drills | Conduct periodic drills for examination response, data extraction, and fraud incident handling; record lessons learned and update procedures. | Art. 133 + Art. 149 | All Licensed Financial Institutions | Compliance | Detective | Operating effectiveness | Drill reports; updated SOPs | Semi-Annual | Medium | 2026-02-08 | 2026-02-05 | Blocked | Red | Blocked due to dependency (system/process/vendor); escalate and agree remediation plan; interim workaround required. | https://example.com/compliance/CBUAE/SUP/SUP-030
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Amber
Formulas:
RAG = IF([Status]="Implemented","Green",IF([Status]="Not Applicable","Grey",IF(AND([Due date]<>"",[Due date]<TODAY()),"Red",IF([Status]="Blocked","Red",IF([Status]="In Progress","Amber",IF([Status]="Not Started","Amber","Amber"))))))

## Dashboard 3 - Supervision
Dashboard 3: Supervision, Reporting & Protection
Linked checklist: Checklist 3 - Supervision
KPI | Value
Total controls | 30
Applicable controls | 30
Implemented | 9
In progress | 7
Not started | 3
Monitoring | 9
Blocked | 2
Overdue (due date passed) | 3
% complete (Implemented / Applicable) | 30%
Status | Count
Not Started | 3
In Progress | 7
Implemented | 9
Monitoring | 9
Blocked | 2
Not Applicable | 0
Owner function | Count
Compliance | 7
Legal | 3
Board Secretariat | 0
Risk Management | 5
Operations | 1
IT/Security | 4
Finance | 2
Internal Audit | 0

## Definitions
Definitions & How to Use This Workbook
Use this tab to interpret tracker fields, statuses, RAG logic, and key regulatory terms used across all three checklists.
Category | Term | Definition | How to use in the checklist / dashboard | Example / Notes
Workbook field | Control ID | Unique identifier for each control/test item (e.g., LIC-001). | Use as a stable reference for audit trails, issue logs, and evidence folders. | Keep unchanged once issued; create new IDs for new controls.
Workbook field | Domain | The compliance theme or process area the control belongs to. | Use to group controls for ownership, reporting, and internal reviews. | Examples: Licensing perimeter, Board approvals, Exam readiness.
Workbook field | Requirement / Control statement | A plain-language statement of what must be in place (policy/process/control). | Write it so a tester can objectively assess it (what, who, frequency, and evidence). | Start with a verb: Maintain / Operate / Evidence / Track / Implement.
Workbook field | Reference (Article/Item) | The clause/article reference that the control maps to. | Use to demonstrate traceability from regulation → internal control. | Keep the same format throughout (e.g., Art. 60(1)-(2)).
Workbook field | Applicability | Defines whether the control applies to the institution and/or which legal entity it covers. | Set to 'Not Applicable' if the control is genuinely out of scope, with rationale in notes. | Example: Non-deposit taker may mark related-party statement as N/A if not required.
Workbook field | Owner function | The accountable team that maintains the control (first line) or oversees it (second line). | Use for escalation and dashboard slicing; keep one primary owner. | Examples: Compliance, Risk Management, Legal, IT/Security.
Workbook field | Control type | Preventive = stops issues; Detective = finds issues; Corrective = fixes issues. | Use to balance the control environment and highlight where preventive controls are missing. | A robust program contains all three types.
Workbook field | Testing method | How you validate the control: Design effectiveness, Operating effectiveness, or Both. | Use 'Design' when the control is being built; 'Operating' when it is running; 'Both' for mature controls. | Design = exists & is adequate; Operating = evidence it worked.
Workbook field | Evidence / artefact | The document(s) or system outputs proving the control exists and is operating. | List the minimum evidence needed so testing is consistent. | Examples: approvals, minutes, registers, logs, reconciliations.
Workbook field | Frequency | How often the control is performed or reviewed. | Align with the risk level and regulatory expectations; use event-driven where triggered by changes. | Quarterly/Monthly/Annual/Event-driven/Continuous.
Workbook field | Priority | Implementation urgency (High/Medium) based on impact and regulatory risk. | Use for sequencing and resourcing; escalate High items that are blocked or overdue. | High often maps to licensing/governance/reporting obligations.
Workbook field | Due date | Target completion or next required completion date. | Used by dashboards to compute 'Overdue' and to manage delivery. | Set realistic internal deadlines; update if formally re-baselined.
Workbook field | Last reviewed | Date the control was last tested or evidence was last refreshed. | Use to demonstrate ongoing monitoring and to plan the next testing cycle. | Avoid leaving blank for controls marked Monitoring.
Workbook field | Status | Current implementation state using the dropdown values. | Update as work progresses; dashboards use Status to calculate counts and % complete. | Do not use free text; keep to dropdown values.
Workbook field | RAG | Traffic-light risk indicator for the control’s current health. | Green = healthy; Amber = needs attention; Red = material gap/issue; Grey = N/A. | Use alongside Status for richer reporting.
Workbook field | Next action / notes | Short plan for closing gaps, maintaining controls, or documenting rationale. | Record blockers, dependencies, and what happens next (incl. approvals and deadlines). | Keep it action-oriented and audit-friendly.
Workbook field | Evidence link | Clickable link to the evidence folder or primary artefact. | Paste your internal repository link (SharePoint/Drive) so testers can access evidence. | Use a folder-per-Control ID pattern.
Status | Not Started | No documented design or operating evidence exists yet. | Use for gaps not yet addressed. | Typical for newly identified obligations.
Status | In Progress | Control is being designed or implemented; partial artefacts may exist. | Use when implementation is actively underway. | Should have a clear next step and due date.
Status | Implemented | Control is implemented and has evidence that it is operating as intended. | Use when you can pass an internal test based on artefacts. | Still requires periodic review based on Frequency.
Status | Monitoring | Control is in place and requires ongoing periodic testing/refresh. | Use when the focus is sustainment rather than build. | Ensure Last reviewed is maintained.
Status | Blocked | Implementation is stalled due to a dependency or constraint outside the owner’s control. | Use when escalation is required; document the dependency in notes. | Examples: awaiting regulator clarification, vendor deliverable, board schedule.
Status | Not Applicable | Control does not apply to the institution’s activities or entity scope. | Use only with a documented rationale in notes. | RAG should typically be Grey.
RAG | Green | On track; evidence exists and no material issues identified. | Use for stable controls meeting requirements. | Dashboards show health at-a-glance.
RAG | Amber | Minor gaps, upcoming deadline risk, or evidence refresh needed. | Use when attention is needed but risk is manageable. | Often paired with Monitoring or In Progress.
RAG | Red | Material gap, overdue item, or control failure identified. | Use for items requiring urgent remediation and escalation. | Often paired with Not Started, In Progress, or Blocked.
RAG | Grey | Not applicable to the institution or entity. | Use only when Status is Not Applicable. | Include rationale in notes.
Dashboard KPI | Total controls | Count of all controls listed in the linked checklist. | Used to size the compliance workload. | Equals number of Control IDs.
Dashboard KPI | Applicable controls | Controls excluding those marked Not Applicable. | Used as denominator for % complete. | Helps avoid skew from out-of-scope items.
Dashboard KPI | Overdue (due date passed) | Count of applicable controls where Due date < today and Status is not Implemented/Monitoring. | Used to flag delivery risk. | If you re-baseline dates, update Due date.
Dashboard KPI | % complete | Implemented ÷ Applicable controls. | Use as a high-level progress metric for management reporting. | Interpret alongside Overdue and RAG.
Regulatory term | License / Licensing | Formal authorization to carry out regulated financial activities under the Central Bank’s framework. | Use in Checklist 1 for scope mapping and change control. | If activity changes, trigger licensing review.
Regulatory term | Licensed Financial Activity | A regulated activity category (e.g., accepting deposits, providing credit, payment services) that requires authorization. | Map each product/service to an activity category in Checklist 1. | Avoid providing/promoting without the required permission.
Regulatory term | Promotion / Invitation to transact | Marketing or facilitating actions that encourage others to enter into regulated financial activities. | Use to control marketing approvals and third-party channels. | Evidence: marketing approval workflow; content review logs.
Regulatory term | Emerging technologies | Technology delivery models (e.g., virtual assets, DeFi mechanisms, platforms/protocols) that can still fall within regulated activity boundaries. | Use the emerging-tech perimeter test controls in Checklist 1. | Evidence: tech risk assessment; governance model; vendor due diligence.
Regulatory term | Authorized Individuals | Individuals in specified senior or controlled roles requiring prior approval and ongoing fitness/suitability. | Use Checklist 2 to track approvals, renewals, and role changes. | Maintain an approval register and succession plan.
Regulatory term | Designated Functions | Key functions/roles that are subject to regulatory fit-and-proper expectations and may be restricted if not suitable. | Use Checklist 2 to monitor fit-and-proper triggers and attestations. | Evidence: screening pack; declarations; training records.
Regulatory term | Fit and proper | Suitability assessment covering integrity, competence, and capability to fulfill a role responsibly. | Use for board nominations and authorized individuals tracking. | Evidence: background checks; CV; declarations; performance concerns.
Regulatory term | Consolidated supervision | Central Bank oversight applied at group level, not only at the standalone entity level. | Use Checklist 3 to maintain group structure, intra-group exposures, and supervisory readiness. | Evidence: group org chart; policies across subsidiaries.
Regulatory term | Prudential directives | Supervisory instructions that can set requirements on capital, liquidity, exposures, and reporting. | Use Checklist 3 to keep a regulatory obligations calendar and evidence pack. | Evidence: regulatory inventory; board reporting.
Regulatory term | Related-party exposures statement | Periodic internal statement/reporting of exposures to related parties for deposit-taking institutions. | Track quarterly preparation, review, and sign-off in Checklist 3. | Evidence: statement, reconciliation, approvals.
Regulatory term | Rulebook | Central repository of applicable regulations/standards issued by the Central Bank. | Assign an owner to monitor updates and keep policies aligned. | Evidence: regulatory change log; update notices.
Regulatory term | Examination / inspection | Regulator’s power to review the institution and require access to records and information. | Maintain an exam-ready evidence pack (Checklist 3). | Evidence: inspection response procedure; data room index.
Regulatory term | Transitional period | A defined period granted to comply with a new requirement. | Use to plan implementation waves and due dates. | Document the transition plan and milestones.