## About_the_Tracker
This ISSB IFRS S2 Amendments Implementation & Assurance Tracker is an implementation and assurance tracker designed to operationalise the ISSB’s targeted amendments to IFRS S2 (GHG emissions disclosures) by translating the requirements into a structured, owner-assigned checklist with due dates, evidence fields, and automated progress monitoring. The Checklist tab breaks the amendments into practical tasks covering key elections (for example, whether to limit Scope 3 Category 15 to financed emissions), methodological choices (such as financed-emissions industry classification), and jurisdictional relief scenarios (alternative measurement methods or GWP values for parts of the entity), while requiring users to document decisions and maintain an audit trail through referenced workpapers. A Dashboard aggregates the checklist in real time to show completion rates, status distribution, and overdue or at-risk items, enabling management to steer delivery and escalate constraints early. Supporting tabs for Owner Map, Definitions, and References ensure clear accountability, consistent terminology, and traceability to primary IFRS/ISSB sources, making the workbook a practical “single source of truth” for execution, governance, and assurance readiness.

## Dashboard
Implementation Dashboard
Update the Checklist sheet (blue input cells). Metrics and charts update automatically.
Overall KPIs
Total tasks | Done | In progress | Not started | Blocked | N/A | Active (excl. N/A) | Completion %
38 | 7 | 10 | 18 | 2 | 1 | 37 | 18.92%
Completion by Amendment Area
Amendment Area | Done | Active (excl. N/A) | Completion %
Amendment A - Category 15 (financed emissions limitation) | 2 | 8 | 25%
Amendment B - Financed emissions industry classification | 3 | 7 | 42.86%
Amendment C - Jurisdictional relief (GHG Protocol method) | 0 | 4 | 0%
Amendment D - Jurisdictional relief (GWP values) | 1 | 5 | 20%
Controls & Assurance | 0 | 6 | 0%
Governance & Adoption | 1 | 4 | 25%
Transition & Comparatives | 0 | 3 | 0%
Status distribution
Status | Count
Done | 7
In progress | 10
Not started | 18
Blocked | 2
N/A | 1
Done vs Remaining (excl. N/A)
Bucket | Count
Done | 7
Remaining | 30

## Checklist
ISSB Targeted Amendments (IFRS S2) - Implementation Checklist
Fill in blue input cells. Use dropdowns for Applies, Election, Status, and Owners. Dashboard updates automatically.
ID | Amendment Area | Requirement / Task | Ref (para.) | Applies? | Election / Decision | Status | Primary Owner | Support Owner(s) | Suggested Timing | Due Date | Evidence / Workpaper Ref | Disclosure Output (Y/N) | Notes | Source (URL)
T01 | Governance & Adoption | Confirm applicability: reporting entity will apply IFRS S2 and these targeted amendments. | General; effective date | Yes | Yes - adopt IFRS S2 + amendments | Done | Sustainability Reporting Lead | Finance (CFO Office); Legal / Compliance | Now | 2026-02-10 | WP-GOV-01 Applicability assessment; Steering Committee minutes (Feb 2026) | Y | Example assumes a listed GCC banking group reporting under IFRS; IFRS S2 will apply for FY2027. | https://www.ifrs.org/news-and-events/news/2025/12/issb-issues-targeted-amendments-ifrs-s2/
T02 | Governance & Adoption | Decide adoption approach: apply from mandatory date or early adopt; document decision and disclose if early adopted. | Effective date/early application | Yes | Mandatory date (FY2027); no early adoption | In progress | Finance (CFO Office) | Sustainability Reporting Lead; Legal / Compliance | Now | 2026-03-15 | Board paper draft: adoption approach + timeline (v0.3) | Y | Decision targeted for March 2026 Audit Committee; disclosure will state adoption date when finalized. | https://www.ifrs.org/news-and-events/news/2025/12/issb-issues-targeted-amendments-ifrs-s2/
T03 | Governance & Adoption | Update reporting manual/policy: document elections, definitions, boundaries, and evidence requirements for audit/assurance. | C1A–C6 (transition) | Yes | N/A | In progress | Sustainability Reporting Lead | Internal Audit / Controls; Data / IT | T-12 to T-9 months | 2026-05-31 | Reporting manual update draft (S2-GHG v1); change log | N | Includes elections, definitions, boundary decisions, and evidence requirements for assurance. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T04 | Governance & Adoption | Update internal control framework: add control points for amendments (Category 15 boundary, classification choice, jurisdictional relief evidence). | Transition; measurement inputs | Yes | N/A | Not started | Internal Audit / Controls | Sustainability Reporting Lead; Finance (CFO Office) | T-12 to T-6 months | 2026-06-30 | Controls design pending | N | Planned to align with FY2026 SOX/ICFR refresh cycle. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T05 | Amendment A - Category 15 (financed emissions limitation) | Assess materiality of Scope 3 Category 15 (Investments) and whether financed emissions disclosures are required (asset mgmt/banking/insurance). | 29(a)(i)(3); 29(a)(vi)(2) | Yes | Material Category 15 for banking + asset mgmt arms | Done | Risk / Model Governance | Finance (Treasury/Investments); Sustainability Reporting Lead | Now | 2026-02-15 | WP-CAT15-01 Materiality memo; portfolio exposure summary | N | Category 15 material due to lending book + AUM; financed emissions disclosure required. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T06 | Amendment A - Category 15 (financed emissions limitation) | Decide whether to apply the permission to limit Category 15 to financed emissions only. | 29A | Yes | Elect to limit Category 15 to financed emissions only | Done | Sustainability Reporting Lead | Finance (Treasury/Investments); Risk / Model Governance | Now | 2026-02-20 | Elections memo section A (signed draft) | Y | Will disclose derivative definition and excluded activities as required. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T07 | Amendment A - Category 15 (financed emissions limitation) | Define financed emissions boundary (loans and investments scope: loans, project finance, bonds, equity investments, undrawn commitments; asset management: AUM). | 29A | Yes | Boundary includes loans, project finance, bonds, listed equity; includes undrawn commitments | In progress | Finance (Treasury/Investments) | Risk / Model Governance; Data / IT | T-9 to T-6 months | 2026-04-15 | WP-FE-01 Boundary map + data sources inventory | N | Asset management: AUM included; will confirm consolidation boundary alignment with financial statements. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T08 | Amendment A - Category 15 (financed emissions limitation) | If applying limitation: confirm treatment of derivatives; determine what is treated as a derivative (align to IFRS/other GAAP used for financial statements). | 29B(a) | Yes | Exclude derivative-associated activities under 29B(a) | In progress | Finance (Treasury/Investments) | Legal / Compliance; Risk / Model Governance | T-9 to T-6 months | 2026-04-30 | Derivatives taxonomy draft; list of in-scope/out-of-scope positions | Y | Definition of ‘derivative’ aligned to IFRS 9/IAS 32 treatment used in financial statements. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T09 | Amendment A - Category 15 (financed emissions limitation) | If applying limitation: describe financial activities excluded from Category 15 measure due to limitation (including activities associated with derivatives). | 29B(b) | Yes | To be finalized after derivatives mapping | Not started | Sustainability Reporting Lead | Finance (Treasury/Investments); Legal / Compliance | T-6 to T-3 months | 2026-05-15 | Disclosure drafting pending | Y | Will describe excluded financial activities (incl. derivative-related) in plain language. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T10 | Amendment A - Category 15 (financed emissions limitation) | Produce Category 15 bridge disclosure: total Category 15 emissions included in Scope 3 and subtotal financed emissions within that total. | 29C | Yes | Bridge disclosure required (29C) | Not started | Sustainability Reporting Lead | Risk / Model Governance; Finance (Treasury/Investments) | T-3 months | 2026-06-15 | Template created; numbers pending | Y | Will report (i) total Category 15 included in Scope 3 and (ii) financed emissions subtotal. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T11 | Amendment A - Category 15 (financed emissions limitation) | Validate that limiting Category 15 does not omit other required disclosures about transition risks/targets where relevant (outside the Category 15 metric itself). | Basis for Conclusions emphasis | Yes | N/A | Not started | Sustainability Reporting Lead | Risk / Model Governance | T-3 months | 2026-06-15 | Impact assessment pending | N | Check that limitation does not affect other required climate disclosures (targets/strategy/metrics). | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T12 | Amendment B - Financed emissions industry classification | Identify where financed emissions must be disaggregated by industry (banking/insurance guidance) and confirm current use of GICS or other taxonomy. | B62A/B63A | Yes | Yes - banking, insurance, asset mgmt activities | Done | Risk / Model Governance | Finance (Treasury/Investments); Sustainability Reporting Lead | T-9 to T-6 months | 2026-02-28 | WP-CLASS-01 Activities inventory + disclosure map | N | Financed emissions disaggregation by industry needed for lending + insurance investment portfolios. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T13 | Amendment B - Financed emissions industry classification | Select an industry classification system that provides useful information about exposure to climate-related transition risks. | B62A(a)(i); B63A(a)(i) | Yes | Banking: GICS (peer comparability); Insurance: NAICS (vendor data) | Done | Risk / Model Governance | Sustainability Reporting Lead; Data / IT | T-9 to T-6 months | 2026-03-05 | Classification selection memo + rationale | N | Selection prioritizes user understanding of transition risk and data availability. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T14 | Amendment B - Financed emissions industry classification | If a commonly used peer/jurisdiction system works equally well, prioritise it over an entity-specific system; document rationale. | B62A(a)(i); B63A(a)(i) | Yes | Prioritize commonly used systems where equally useful | Done | Risk / Model Governance | Sustainability Reporting Lead | T-9 to T-6 months | 2026-03-05 | Peer benchmark summary (5 local banks) | N | Example shows preference for commonly used classification systems when equivalent. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T15 | Amendment B - Financed emissions industry classification | Document if different classification systems are used across activities (e.g., banking vs insurance) and ensure consistent mapping controls. | B62A(a)(i); B63A(a)(i) | Yes | Different systems by activity permitted; document controls | In progress | Risk / Model Governance | Internal Audit / Controls; Data / IT | T-6 months | 2026-04-01 | Mapping controls draft (owner, change approval, versioning) | N | Will implement change log and periodic reconciliation between systems. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T16 | Amendment B - Financed emissions industry classification | Disclose classification system used and explain how selection meets requirements. | B62A(a)(ii); B63A(a)(ii) | Yes | Disclose system + rationale in notes | Not started | Sustainability Reporting Lead | Risk / Model Governance | T-3 months | 2026-07-15 | Disclosure note pending | Y | To be drafted alongside FY2027 IFRS S2 note package. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T17 | Amendment C - Jurisdictional relief (GHG Protocol method) | Inventory regulatory/exchange requirements for GHG measurement methods across jurisdictions where the group operates and listings. | 29(a)(ii); B24 | Partial | Regulator requires alternative method for one subsidiary only | In progress | Legal / Compliance | Sustainability Reporting Lead; Data / IT | Now | 2026-03-10 | Regulatory register extract + interpretation memo | N | Example: one regulated subsidiary follows local method; rest of group uses GHG Protocol. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T18 | Amendment C - Jurisdictional relief (GHG Protocol method) | If different method is required for only part of the entity, define boundary (entities/segments) and apply required method to that part only. | B24 clarification | Partial | Apply alternative method only for regulated subsidiary; document boundaries | Blocked | Legal / Compliance | Sustainability Reporting Lead; Finance (CFO Office) | T-9 to T-6 months | 2026-04-10 | Awaiting exchange clarification letter | N | Blocked pending written confirmation on scope (legal entity vs activity-level requirement). | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T19 | Amendment C - Jurisdictional relief (GHG Protocol method) | Evidence pack: retain legal/regulatory basis, scope of application, and mapping of segments/entities to measurement method. | B24 clarification | Partial | N/A | Not started | Legal / Compliance | Internal Audit / Controls | T-6 months | 2026-05-01 | Evidence pack to be assembled | N | Will retain legal basis, scope map, and reconciliation approach for assurance. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T20 | Amendment D - Jurisdictional relief (GWP values) | Confirm whether emissions are measured via direct measurement and/or emission factors; identify whether emission factors are already in CO2e. | B21–B22 | Yes | Mix of direct measurement + emission factors | Done | Data / IT | Sustainability Reporting Lead | T-9 to T-6 months | 2026-02-25 | GHG inventory methodology note + source list | N | Identified which sources provide CO2e vs constituent gas data. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T21 | Amendment D - Jurisdictional relief (GWP values) | If direct measurement: confirm latest IPCC AR GWP (100-year) would be required absent jurisdictional rules; document approach. | B21–B22 | Yes | Baseline: latest IPCC AR (100-year) for direct measurement | In progress | Sustainability Reporting Lead | Data / IT; Legal / Compliance | T-9 to T-6 months | 2026-03-20 | GWP values control table (draft) | N | Will confirm latest IPCC AR version referenced in methodology and lock values for reporting year. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T22 | Amendment D - Jurisdictional relief (GWP values) | If jurisdiction/exchange requires different GWP values (whole or part), apply those values to the affected part only; document boundary. | B21–B22 relief | Partial | Use regulator-required GWP values for one subsidiary only | Blocked | Legal / Compliance | Sustainability Reporting Lead; Data / IT | T-6 months | 2026-03-25 | Regulator rule confirmation pending | N | Example assumes regulator mandates older GWP values for regulated entity; pending formal citation. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T23 | Amendment D - Jurisdictional relief (GWP values) | Evidence pack: retain jurisdiction/exchange requirement and demonstrate how GWP values are applied per boundary over time. | B21–B22 relief | Partial | N/A | Not started | Legal / Compliance | Internal Audit / Controls; Data / IT | T-6 months | 2026-04-15 | Evidence pack to be assembled | N | Store rule text, scope mapping, and calculation screenshots for assurance traceability. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T24 | Transition & Comparatives | If previously applied IFRS S2: assess whether comparative adjustments are required and practicable (method relief, GWP relief, Category 15 bridge, classification system). | C6 | Yes | Previously applied IFRS S2 in FY2026 (pilot) | Not started | Sustainability Reporting Lead | Finance (CFO Office); External Assurance Liaison | T-6 to T-3 months | 2026-09-30 | Prior-year pilot package | N | Example assumes prior-year pilot disclosures exist; comparatives assessment required. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T25 | Transition & Comparatives | Adjust comparative information unless impracticable; document any impracticability assessment and disclosures. | C6 | Yes | Restate comparatives unless impracticable | Not started | Finance (CFO Office) | Sustainability Reporting Lead; Internal Audit / Controls | T-3 months | 2026-11-30 | Comparatives assessment template | Y | Document impracticability rationale if any (systems, data availability, boundary changes). | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T26 | Controls & Assurance | Establish version-controlled calculation workpapers for financed emissions and Category 15 disclosures with traceable inputs and assumptions. | General | Yes | N/A | In progress | Risk / Model Governance | Data / IT; Finance (Treasury/Investments) | T-6 months | 2026-06-30 | WP-FE-Calc-01 (versioned workbook); QA checklist draft | N | Set up reproducible calculations and version control for financed emissions workpapers. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T27 | Controls & Assurance | Implement review controls: tie-outs between portfolio exposure data, classification mapping, and disclosed financed emissions tables. | General | Yes | N/A | Not started | Internal Audit / Controls | Risk / Model Governance; Finance (CFO Office) | T-6 months | 2026-08-31 | Control design pending | N | Tie-outs to portfolio exposures, mapping tables, and disclosure tables will be control points. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T28 | Controls & Assurance | Confirm alignment with consequential SASB amendments where SASB metrics are used as industry-based guidance or referenced in reporting. | Consequential SASB amendments | No | N/A | N/A | Sustainability Reporting Lead |  | T-6 months |  | N/A | N | Example: entity not using SASB Standards; consequential SASB amendments not applicable. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-consequential-amendments-ifrs-s2.pdf
T29 | Controls & Assurance | Prepare assurance pack: decisions memo, boundary maps, regulatory requirement register, control evidence, and final disclosure tie-outs. | General | Yes | N/A | Not started | External Assurance Liaison | Sustainability Reporting Lead; Internal Audit / Controls | T-1 month | 2026-10-31 | Assurance pack index (template) | N | Will include decisions memo, boundary maps, rule citations, and signed control evidence. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T30 | Amendment A - Category 15 (financed emissions limitation) | Confirm which asset classes are included in financed emissions calculations and whether any additional asset classes will be included; document why any additions are relevant. | B62A(b)/B63A(b) (asset class relevance) | Yes | Asset classes: corporate loans, project finance, sovereign bonds, listed equity; include undrawn commitments | In progress | Risk / Model Governance | Finance (Treasury/Investments) | T-6 months | 2026-05-31 | Asset class scope note + relevance rationale | Y | If adding any asset classes beyond specified guidance, document relevance as required. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T31 | Amendment B - Financed emissions industry classification | Set up mapping governance (data dictionary, mapping ownership, change log) for the selected classification system and portfolio counterparties/investee data. | B62A/B63A | Yes | N/A | In progress | Data / IT | Risk / Model Governance | T-6 months | 2026-06-15 | Data dictionary draft; ownership matrix | N | Defines mapping ownership, change approval workflow, and periodic refresh schedule. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T32 | Amendment B - Financed emissions industry classification | Back-test disaggregation results under the selected system vs prior system (if changed) to identify and explain material shifts. | B62A/B63A; C6(c) | Yes | N/A | Not started | Risk / Model Governance | Sustainability Reporting Lead | T-3 months | 2026-08-15 | Back-test plan | N | Back-test new classification system vs prior year; quantify material shifts and explain. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T33 | Amendment C - Jurisdictional relief (GHG Protocol method) | Update methodology disclosure: clearly state where alternative methods are used and which parts of the entity are affected. | 29(a)(ii); B24 | Partial | N/A | Not started | Sustainability Reporting Lead | Legal / Compliance | T-3 months | 2026-12-15 | Methodology note update pending | Y | Disclose where alternative measurement method applied (which entities/segments) and why. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T34 | Amendment D - Jurisdictional relief (GWP values) | Update methodology disclosure: clearly state where jurisdiction-required GWP values are used and which parts of the entity are affected. | B21–B22 | Partial | N/A | Not started | Sustainability Reporting Lead | Legal / Compliance; Data / IT | T-3 months | 2026-12-15 | Methodology note update pending | Y | Disclose where jurisdiction-required GWP values used and confirm emission factors CO2e treatment. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T35 | Transition & Comparatives | Design disclosure note for comparative restatements (or impracticability) and obtain governance sign-off (CFO/Sustainability Committee). | C6 | Yes | N/A | Not started | Finance (CFO Office) | Sustainability Reporting Lead | T-2 months | 2026-12-31 | Disclosure note draft pending | Y | Governance sign-off required for comparative restatement/impracticability disclosures. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T36 | Controls & Assurance | Run a dry run close: produce draft disclosures, perform internal review (Finance/Sustainability/Risk), and resolve gaps before period-end. | General | Yes | N/A | Not started | Sustainability Reporting Lead | Internal Audit / Controls; External Assurance Liaison | T-2 months | 2026-12-20 | Dry run close checklist (template) | N | Dry run will test end-to-end workflow and identify evidence gaps before year-end close. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf
T37 | Controls & Assurance | Assurance readiness: ensure all URLs and reference docs are archived internally and accessible to assurance providers. | General | Yes | N/A | Not started | External Assurance Liaison | Data / IT; Internal Audit / Controls | T-1 month | 2026-12-20 | Archive procedure draft | N | Ensure all sources (URLs, rule docs) are archived; preserve version trail for assurance. | https://www.ifrs.org/news-and-events/news/2025/12/issb-issues-targeted-amendments-ifrs-s2/
T38 | Controls & Assurance | Update disclosure controls checklist to include new paragraph references (29A–29C, B62A/B63A, B21–B22, B24, C6). | 29A–29C; B21–B22; B24; B62A/B63A; C6 | Yes | N/A | Not started | Internal Audit / Controls | Sustainability Reporting Lead | T-3 months | 2026-12-31 | Disclosure controls checklist update pending | N | Update controls to include new paragraph references and tie-out steps. | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf

## Owner Map
Owner List | Workstream Ownership Map
Owners (use for dropdowns) | Workstream / Deliverable | Primary Owner | Key Inputs | Output / Evidence
Sustainability Reporting Lead | Elections memo and reporting policy | Sustainability Reporting Lead | CFO Office; Legal; Risk | Signed policy memo; disclosure elections
Finance (CFO Office) | Category 15 boundary and exclusions | Finance (Treasury/Investments) | Portfolio data; methodology | Boundary map; exclusions narrative; derivative definition
Finance (Treasury/Investments) | Financed emissions calculations | Risk / Model Governance | Counterparty/investee data | Workpapers; QA checks; reproducible logs
Risk / Model Governance | Industry classification mapping | Risk / Model Governance | Selected taxonomy; portfolio mapping | Mapping table; change log; rationale
Data / IT | Jurisdictional method and GWP overrides | Legal / Compliance | Regulatory/exchange rules | Rules register; scope mapping; override controls
Legal / Compliance | Disclosure drafting and tie-outs | Sustainability Reporting Lead | All workstreams | Draft notes; tie-outs to workpapers
Internal Audit / Controls | Assurance readiness pack | Internal Audit / Controls | Control evidence | Control matrix; sign-offs; version trail
External Assurance Liaison
Business Unit Lead

## Definitions
Key Definitions (edit as needed)
Term | Definition / Notes | Owner (optional)
Scope 3 Category 15 (Investments) | GHG emissions associated with investments (Category 15) as part of Scope 3. Under the amendments, entities may limit Category 15 measurement/disclosure to financed emissions only, if they choose.
Financed emissions | Portion of gross emissions of an investee/counterparty attributed to loans and investments made by the entity (includes loans, project finance, bonds, equity investments, undrawn commitments; for asset managers, AUM).
Derivative (for Category 15 limitation) | Define consistently with IFRS Accounting Standards or other GAAP used for financial statements; disclose what you treated as a derivative when applying the limitation.
Industry-classification system (financed emissions) | Taxonomy used to disaggregate financed emissions information by industry. Select a system that enables useful transition-risk insight; prefer commonly used systems where all else equal.
GHG Protocol Corporate Standard (2004) | Baseline measurement method required by IFRS S2 unless jurisdiction/exchange requires a different method (whole or part).
Global Warming Potential (GWP) values | Used to convert constituent gases to CO2e. Baseline is latest IPCC Assessment Report (100-year) for direct measurement unless jurisdiction/exchange requires different GWP values (whole or part).
Jurisdictional relief (partial-entity) | Relief applies when a regulator/exchange requirement applies to only part of the entity; alternative method/GWP may be used only for that part for as long as requirement applies.
Comparative adjustments / impracticable | If previously applied IFRS S2, adjust comparatives unless impracticable; document and disclose approach.

## References
References (primary sources)
Title | URL | Notes
ISSB news release: targeted amendments to IFRS S2 (11 Dec 2025) | https://www.ifrs.org/news-and-events/news/2025/12/issb-issues-targeted-amendments-ifrs-s2/ | Summary of amendments and effective date
ISSB 2025-1: Amendments to IFRS S2 (Amendments to GHG Emissions Disclosures) | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-amendments-ifrs-s2.pdf | Authoritative amendment text; 29A–29C, B21–B22, B24, B62A/B63A, C6
ISSB 2025-1: Consequential amendments to align SASB Standards | https://www.ifrs.org/content/dam/ifrs/publications/amendments/english/2025/issb-2025-1-consequential-amendments-ifrs-s2.pdf | Financed emissions metrics aligned to amended IFRS S2